## Hitachi
|  | Check Point | Owener | Reviewer-1 | Reviewer-2 | Remain work | Target Date | Progress | Evidence | How shared
Over All | Current status - completed setting up test environment - completed 28 cases of 72 total cases. Report and evidence in SVN (github) Plan: - Expecting to complete tests by Tue end of our day. (stretch tests not included) Other action items: - Neominds team shall report progress everyday along with evidence for tests - Neominds team will try to setup a windows based environment and try to run few sanity tests - All documents and screen shots to be checked for any mention of incorrect version | Test result summary report Test evidence | Jayesh Babu | Hiroyuki Nakayama | Shigeru Shimizu |  | 20/9 | 28/72 | console log | svn(github)
Environment | Development Host | Version of N/W stack as same as Design Note | Jayesh
| Target Board | Version & configuration | Gopika S | Jayesh |  |  |  | confirmed
| Networksimilator | Version & configuration | Gopika S | Jayesh |  |  |  | confirmed
Implementation | N/W simulator | cover all requirements | Jayesh | Gopika S |  |  |  | confirmed
| Target Board | cover all requirements | Jayesh | Gopika S |  |  |  | confirmed
Test Case | Check w/ N/W simulator | all cases PASS | Gopika S | Jayesh
| Check w/ Target Board | all cases PASS | Gopika S | Jayesh
| Check w/ N/W simulator and Target board | all cases PASS | Gopika S | Jayesh
Documentation | Design Note-English | correct version, no document error | Jayesh | H Nakayama | [5 empty] | svn(github)
| Design Note-Japanese | correct version, no document error | H Nakayama | S Shimizu | [5 empty] | svn(github)
| ATP(Test Spec)-English | correct version, no document error | Gopika S | Jayesh | [5 empty] | svn(github)
| ATP-Japanese | correct version, no document error | H Nakayama | S Shimizu | [5 empty] | svn(github)
| ATPR(Results)-English | correct version, no document error | Gopika S | Jayesh | [5 empty] | svn(github)
| ATPR-Japanese | correct version, no document error | H Nakayama | S Shimizu | [5 empty] | svn(github)
| Release Note-English | correct version, no document error | Jayesh | H Nakayama | [5 empty] | svn(github)
| Release Note-Japanese | correct version, no document error | H Nakayama | S Shimizu | [5 empty] | svn(github)
Images | Docs | correct version, no document error | Gopika S | Jayesh | [5 empty] | svn(github)
| Source | correct path, version | Jayesh | H Nakayama | [5 empty] | svn(github)
| Binay | both simulator and target | Jayesh | H Nakayama | [5 empty] | svn(github)
| Evidence | for all tests | Gopika S | H Nakayama | [5 empty] | svn(github)
Label

## FX Palacious
| Status | Summary | Reproduction | Analisys | Counter | Make Solution | Deliver customer | Documentation | Target Date | Progress | Evidence | How shared
A) Bad mode issue during suspend-resume (top-priority) - Checked bad_mode after switching to 115200 - Issue not seen. - PCIe GBE disabled and checked for bad_mode issue - Not seen in this scenario too - Applied USB patches and created new kernel image - Issue still observed. B) USB1.1 device not detected [FIXED] - device wasn’t detected because of OHCI disabled in kernel tree - When OHCI enabled in device tree, USB1.1 device is recognized, but results in bad_mode. - Nakayama-san Enabled OHCI and tried image with patch on GISMO. USB1.1 works without bad mode issue. Neominds team to try the same Image offshore and check if bad mode is seen during suspend-resume. C) Quad SPI not working - Quad SPI not enabled because chip_select variable in driver structure is not set. This requires platform data In the driver to be filled up. More study is required to find out why platform data is missing information. D) SPI clock speed not set to maximum Not started. Plan: A) - continue investigation/debugging bad mode issue - recheck if usb patch fixes bad mode issue in suspend-resume scenario (also received Image from Nakayama-san) - check timers in device drivers for serial and SPI as potential candidate for bad mode issue - check cache invalidate/evict inconsistency or possible delay during suspend-resume - check CPU wake-up sequence during resume for possible out of sync with cache operations - Try to identify task/thread causing exception during resume - compare resume activity sequence in kernel with baud rates 38400 and 115200 C) - continue investigation/debugging issue - Investigate reason for platform_data not available to enable Quad-SPI mode in SPI driver D) - start working on issue - Find out actual clock speed at which SPI is set to operate in kernel/driver configuration
Bad Mode Issue after resume |  | Update: 9/18: bad_mode: tried with Image Nakayama-san prepared with USB patches. Bad_mode during suspend-resume still observed. Investigated exception vectors and code changes from WR product team. Currently checking possibility of restoring pre-exception state during suspend-resume without causing panic(). Jacob to share relevan to console logs of debugging | [8 empty] | Jacob will share console logs
SPI Baud rate
SPI Speed / clock
Customer's USB 1.1 HUB |  | Fixed